## Slide 1: ENI CBC project planning
Key aspects of project activity and financial planning
Black Sea Basin programme, Project preparation workshop
[Place], [Date]
Notes: Financial and activity planning aspects, including planning monitoring and communication activities: capacity building presentations (link to evaluation criteria 6 to 8)

## Slide 2
Who, what, when, how: building a good work plan
How much, when: budget development and planning
How will YOU know you’re achieving your objectives: planning monitoring and evaluation activities
How will THEY know what your project is achieving: planning communication, visibility and capitalisation activities
What about after the project: planning sustainability
What can you do when you’ve answered these questions?
Planning the implementation of ENI CBC project
Notes: Intro to plan of session
Can include mention that will hear from experienced project partner or mention of a small group work as appropriate

## Slide 3: Who, what, when, how? Building a good work plan

## Slide 4
Work plan
Consistent
It should be consistent with the planned outputs
Transparent
It should provide sufficient information and detail
Logic
It should demonstrate the work flow and how activities build on each other
Concrete and sustainable
It should identify concrete target groups and foresee provisions for sustainability and transferability
Basics of work plan development
Notes: Notes for the trainer:
You should stress the link with the logframe: the work plan/work package is focused on activities designed to achieve outputs which in turn result in the achievement of specific objectives leading to overall objectives.
These are also the elements the assessor will check base on the award criteria of the evaluation grid as explained in the following slide

## Slide 5
Work plan: group of activities approach
3 Minimum GAs
Project management
(1 GA)
Communication
(1 GA)
Implementation
(1 or several GAs based on number of outputs/results)
Investment
(0 or 1 GA)
Group of related activities organised based on dependencies and interdependencies:
“What needs to be done first in order to do this next”
Notes: Notes: a project requires several work packages to be completed. Three is generally the minimum in order to cover the essential work:
General project management: all the activities necessary to coordinate the work of the partnership, to monitor it, to verify expenditure, to report it to the programme and oversee the general implementation of the project.
  SOME PROGRAMMES propose a list of potential activities (MSB) List: Strategy building and updating (annual plans), Set up of contact databases, Coordination/provision of communication contents (from/to projects, from/to programme), Social media communication, Communication materials (posters, flyers, etc), Events organisation (thematic community’ events with projects, kick off meeting. Mid-term and final events, etc), Events participation events (thematic working groups, project meetings, coordination events with programme bodies, public events, etc), Project website, Project logo and image, Communication Training and seminars, Presentation/exhibition at external events (e.g. with projects, other cluster etc), Communication with media, Production and update of publications (print and online), Others (please specify).
Communication: all the activities necessary to ensure targeted awareness about the project workand achievements outside the project partnership.
  SOME PROGRAMMES propose a list of potential activities (MSB): List: Communication Plan and annual communication updates, Target group mapping and contact databases, Online publications (online newsletters or video news, infographic, flip books, smart phone application etc.), Print publications (brochures, leaflets, flyers), Event follow-up material (conclusions, recommendations, video reporting, interviews live streaming), Exhibition and promotion material, Media//press kit (texts, pictures), Website, Project image design, Website and social network, Dissemination and promotional products, Other (please specify)
Implementation/Technical work: this work package clusters the project specific activities. A project may establishas many thematic work packages as necessary in order to carry out all necessary activities to deliver the outputs and achieve the objectives. On average, a project will have 3-5 such work packages.
  Identification of key players/elevant EU financed programs/ existing national and regional programs, Community dialogue and meeting, Networking, Clustering, Training/seminar, Mentorship, Recruitment, Coaching, Feasibility study, Identification of business ideas, Baseline survey, Steering Committee, Capitalisation event/forum (research and planning), Study visits, Existing situation analysis (ESA), Good practice report, Strategic models development, Pilot initiatives, Dissemination of results/initiatives/lessons learned, Strategy design, Technology transfer, Sensitisation and public awareness events, Internal Monitoring of Activities, Memory of understanding, Action Plan development, Improvement of regulations (local, regional, national), Recruitment, Data collection, Stakeholders analysis, GIS development, Socio Economic Analysis, Sampling campaign,

## Slide 6
Developing the Work Plan: main steps
Step 1: transfer the main activities, related deliverables and outputs from project logic of intervention
Step 3: estimate the duration, start and end date of each activity
Step 4: coordinate all activities within the timeline and develop a final schedule
Step 5: identify partners and staff responsible for implementing activities
Step 2: detail further the activities as needed
Notes: Note for the trainer :
Step 1: building on work done from previous session
Step 2: detail further in particular management and communication activities (as during previous session worked only on implementation part)

## Slide 7
Project work plan: key questions
Project work plan defines processes and responsibilities
Who will do what? Which partner is going to take care of which part of the work? How are partners going to work together?
How to plan the work needed to achieve deliverables/ outputs?
By when ?
Project partners and programme officers will refer to the work plan during the entire period of implementation to see whether the project is on track
Notes: Notes: the project intervention logic has already defined the activities and outputs : the work plan will organise them in a logical timeline and a consistent process.

## Slide 8
How detailed should the project work plan be?
Can you manage it?
Avoid breaking down your work packages into too many activities: it is time consuming and will be difficult to monitor during the implementation
Is your plan clear ?
Avoid statements that are too vague: they will prevent the partners from having a clear understanding of what it is expected of them, and the programme from understanding what you want to do
Is your plan flexible?
Planning into precise detail what each partner will do for the next 24 or 36 months will almost certainly be inaccurate after just a few weeks
Use your common sense
Notes: At this stage let’s hear from an experienced project partner on hints and what they feel is most important in developing a good workplan

## Slide 9
Project time plan: some hints
Administrative procedures are often time-consuming
Check the number of activities which run in parallel or consequently
Devote appropriate time to promote the final project outputs and results before project end
Collecting data can be uneven across the regions and time consuming
Plan a soft start to the project because start-up activities will take time
In case of Project investments take into account the delays of public procurement procedures
In the Application form, the overall project time line in a Gantt chart is automatically generated on the basis of information inserted in the work plan
Notes: Some further hints on time plan

## Slide 10: How much, when? Budget development and planning

## Slide 11
Activity and financial planning: be consistent!
Allocate resources
Estimate of the resources needed to implement the planned activities:
Cash flow needs!
  You have to calculate the financing you need from the programme and your own co-financing to carry out the planned activities
Project assessment
  Don’t forget you’ll need to cover the possible "gaps" in the cash flow (possible gaps in time between submission of the report and transfer of the next pre-financing instalment): mind the procurement timing!
Be cost-effective: the Programme will assess if your budget reflects sound financial management, in particular economy and efficiency
Do not underestimate, as in case of project approval you will need to deliver expected project outputs and results with the proposed budget
Do not overestimate, both in terms of duration of activities and associated budget
Notes: The work plan also has to take into account the financial plan of the project (and vice versa of course), i.e. that the activities planned are in line with the available financial resources and if the institutions do not have spare resources to "fill in the gaps", probably the activity plan needs to be changed/ adjusted so that they can manage it from the financial perspective as well.
Do not overestimate, as during assessment you project will be compared with others
As regards gaps: mind the timing of procurement (big expenditure has to match some financing)
Remind definitions of economy and efficiency

## Slide 12
Budget development
Based on the planned project activities
=> divide them into the cost items necessary for the implementation of the activities
Gather information from all partners
=> keep in mind that costs for the same item/ service may vary from country to country
Base your cost estimates on realistic costs
=> if necessary, make a market/ price research to establish realistic unit costs
Define the necessary costs
=> do not forget the human resources that need to be involved!
Notes: At this stage let’s hear from a experienced project partner on hints and what they feel is most important in developing the budget

## Slide 13
Nota bene!
Information dissemination
Expenditure verification
Supervision
Participation in programme events
Communication activities
Project evaluation
Project visibility
Do not forget to include into the project budget the following costs that might also be needed for the implementation of the project!
Notes: This slide should be adjusted in line with the programme requirements, e.g. for some programmes expenditure verification can be for free

## Slide 14: How will you know you’re achieving? Planning monitoring and evaluation

## Slide 15
WHAT IS THE DIFFERENCE BETWEEN THE TWO?
  Monitoring is critically following progress: are we still on track?
  How much have we spent (time, money, days)?
  Are activities implemented in time, any bottlenecks?
  Are all planned deliverables and outputs delivered in time, at reasonable cost?
  Are we reaching the target groups (how many)?
  Are we achieving results?
  Evaluation is analysis and judgment: should we change course?
  Uses criteria (relevance, efficiency, effectiveness, impact, sustainability)
  Gives recommendations to improve planning or implementation
  Bad monitoring leads to bad evaluation!
Monitoring and Evaluation
Notes: Notes for trainers (suggested comments):
Explain that evaluation is best done by someone objective and independent as it is to some extent subjective. The roles of the types of evaluation are different: critical check (ex ante: is this going to work?), making possibly needed changes to get back on track (interim), learning (expost: what should we do differently next time?)
If problem detected during monitoring, maybe good time for evaluation to understand the causes and get recommendations!

## Slide 16
MONITORING YOUR PROJECT PROGRESS BASED ON INDICATORS
  The goal of your monitoring is not reporting!
  It should be the systematic and regular review of the execution of activities in order to make key management decisions
  Make sure you know what kind of decisions will have to be taken in advance and what kind of information you need
  Integrate monitoring activities in your project meetings’ agenda
  Create a simple database of inputs (money, time, days), activities (who does what and when), outputs and results, using your indicators
  Find a simple way to visualise the difference between planned and real
  Also include possible risks and assumptions
  Lead Partner is responsible for the system and preparing decisions, the partners for providing quality data in time
  In your own interest: issue Early Warnings ASAP to the MA
Monitoring based on indicators
Notes: Notes for trainers (suggested comments): you may even create a shared Google Drive spreadsheet where partners can insert real-time data on activities etc. This will enable you to prepare and make informed decisions in time and reduces the effort of creating progress reports for the MA.
Note that no indicators requested in application form other than programme indicator, but need to describe still monitoring and evaluation arrangements (proportionate to project) – is assessed!
On early warnings: this is an informal signal to the MA that your project is experiencing a serious problem, which is threatening to delay the project (or part of it) considerably, a key risk associated with one of your assumptions is materialising or for some reason you are spending much more or less money than expected, or you are falling behind with your outputs and don’t think this can be corrected. In fact you can ask the MA for advice or maybe even help. It is your mutual interest to get your project back on track.

## Slide 17
EXAMPLES OF PROJECT INDICATORS
Examples of indicators
  Input: the number of person-days used
  Output: nr of persons participating in environmental actions
  Input: the amount of funds spent per trainee
  Output: square metres of exhibition space renovated
  Output: Nr of additional ICT based tools developed supporting CBC
  Result: number of visitors to sites of cross-border interest
  Result: % of blue flag beaches in the area
  Result: higher rating of availability CB trade info (survey)
  Impact: Income from tourism in municipalities involved
  Impact: Number of cases of recreational water illnesses reported
Notes: This slide only gives possible examples of project indicators NOT to be mentioned in application form as only programme indicators should be mentioned, but to illustrate some indicators projects may develop for internal monitoring

## Slide 18: How will they know what your project is achieving? Planning communication, visibility and capitalisation activities

## Slide 19
Don’t forget to tell your partners!
Internal communication among the project partners
Common planning
Allocation of resources
Project monitoring
Common decision-making
Coordination of project activities
Notes: Internal communication aims to ensure that the project is implemented properly, based on the plan and within the time and budget allocated to it. On the daily basis this communication can be rather informal (phone calls, emails, skype), but it can also take more formal appearance (agreements between the partners, exchange of official letters regarding project changes, minutes of the meetings, etc.).

## Slide 20
Project external communication
External communication with the target groups, project stakeholders and the wider public
Building a common understanding
Raising awareness
Information about the achievements
Accountability
Involvement of target groups
Notes: A communication channel that is relevant to the particular group has to be selected, e.g. youngsters can be reached using social media or website, whereas the seniors will need a different channel to pass the message through to them.
At this stage let’s hear from an experienced project partner on hints and what they feel is most important in internal/external communication

## Slide 21
What is capitalisation?
Capitalisation
(Re)use of knowledge gained and of the project results
Deliver inputs to future strategy and project development
Transfer of the thematic knowledge generated by the project to the policy-makers
Use of available knowledge to improve project practices

## Slide 22
How and what to capitalise?
Keep contact with the policy makers
Keep in touch with projects addressing similar challenges
Support others in use of the results produced by you
Use the available knowledge to develop new projects
Share and promote solutions developed in your project
Build a network of partners interested in your project theme
Notes: There are activities here that the projects can do themselves, as well as those which will be initiated by the programme and where the projects will be asked to participate

## Slide 23: What about after the project? Planning sustainability

## Slide 24
Planning sustainability at design stage
Are the project activities in line with the regional and local strategies?
Are project outputs and results easy to maintain? Is it clear who will take care of it?
Will the facilities created continue to operate? Who will finance them?
Will the project outcomes and results be further promoted and used?
How will the network created among the institutions participating in the project continue to work?
Notes: One might say – if sustainability comes after the end of the project, why do we have to care for it and plan it already now? There are issues that can be addressed only before the project start, e.g. if the project foresees creation of a data base, it is important to plan from the onset how feeding and maintenance of this data base will take place after the project finalisation, if there will be financial resources available to hire external services for this, or if the design of the DB has to allow for the in-house data input and maintenance.
Give examples from different types of sustainability:
Examples of the types of the sustainability:
Social – continued provision of the services to the target area population;
Financial – continued availability of resources to the initiatives started by the project;
Political – continued support from the national/ regional level to the initiatives caused by the project;
Institutional – continued institutional support and involvement into the initiatives started by the project.
Financial sustainability - financing of follow up activities and/or investments, allocation of funds from different sources, resources for covering future operating and/or maintenance costs, etc.
Institutional sustainability - "ownership" of project outputs - which structures (involved in the project) will allow the results of the project to continue to be in place after the project ends? How will this be created?
Political sustainability (only if applicable) - what structural impact will the project have? e.g. will it lead to improved policies, legislation, plans, codes of conduct, methods, etc.?

## Slide 25: What can you do when you’ve answered these questions?
Notes: Review project intervention logic and integrate considerations above

## Slide 26
Working on your project proposal
  1. Draft relevant parts of the application form
  2. Check compliance towards selection criteria
Section D – Work plan
Quality assessment (Award criteria) | Score
Operational assessment criteria (%) (Selection criteria) maximum 45 | 
5. Partnership capacity (to what extent has the partnership the experience and capacity to implement the project?) | 12
6. Communication (To what extent are information and communication activities appropriate and able to reach the relevant target groups and stakeholders?) | 6
6.1 Information and communication activities are clearly defined and linked to the project specific objective | 2
6.2 Information and communication activities are appropriate to reach the relevant target groups and stakeholders | 2
6.3 All the proposed information and communication activities are necessary and proportional with project activities as a whole | 2
7. Work plan (To what extent is the work plan realistic, consistent and coherent?) | 15
7.1 Proposed activities are eligible, realistic, consistent and lead to the planned main outputs and results | 3
7.2 Activities and outputs are in a logical time-sequence | 3
7.3 Time plan is realistic for the proposed activities | 3
7.4 Distribution of tasks among partners is clear, logical, in line with partners’ role in the project and their competencies | 3
7.5 Monitoring and evaluation arrangements are foreseen and appropriate for the project size | 3
8. Budget (To what extent does the project budget demonstrate value for money and is coherent with the work-plan and proportionate?) | 12
8.1 Project budget is correlated with the proposed activities and realistic to the proposed work plan and the main outputs and results envisaged | 6
8.2 The costs included in the project budget are eligible, reasonable, justified and comply with the requirements of sound financial management, in particular regarding economy and efficiency | 4
8.3 Calculation of flat rate for office and administrative costs is correct, is within the maximum limit and costs are reasonable | 2
Work plan
D.1 Group of activities
Management
Implementation
Communication
Investment , if applicable
D.3 Periods
Section | Application
E | Budget
 | Project budget per period
 | Partner budget
 | Activities outside
 | Project Breakdown budget
F | Project budget overview
      Sections E/F – Project Budget
Notes: Note to trainer:
(1): highlight the relevant parts of the work plan to be further designed compared with previous work done (e.g. not D2 target groups but D3 period) and section E/F
(2): link to relevant parts of selection criteria – in previous presentation was strategic assessment criteria (55 points), now work on the operational assessment criteria (45 points) – some about partners capacity itself, but 6 to 8 about quality of communication (mention handout on communication plan), work plan and budget – without goint too much into detail, highlight the importance to defining well these, to check that have included appropriate information to get good scores!). The idea here of course is not that they can read the document on the slides (already presented in MA presentation), but just to visualise the reference to the document.