## Risk register
RISK MATRIX
Name of project beneficiary
Name and acronym of the project
Project code
Period covered (from - to)
File reference
Cross-reference to other documents or working papers
# | Description of risk | Comments by the auditor | Likelihood1 | Consequence2 | Assessment3
1 | Financial report non-reliable |  | Rare
2 | Expenditure non-compliant | Some ineligible expenses detected (staff costs), partner likely has poor understanding of the programme eligibility rules | Likely | Moderate | High
3 | Procurement non-compliant
4 | Revenue non-declared | Project activities do not have potential for revenue | Rare | Marginal | Low
5 | Fraud and corruption present
(add rows if you identify specific risks)
| Prepared by: |  | Name, Position, Signature, Date
| Revised by: |  | Name, Position, Signature, Date
(1) Likelihood: rare, unlikely, possible, likely or almost certain
(2) Consequence: marginal, minor, moderate, major or severe
(3) Assessment: medium, high or critical (according to combination of likelyhood and consequences, as shown in table below)

## Example
MODULE 2: EXAMPLE OF FILLED-IN RISK REGISTER TEMPLATE FOR PROJECTS
# | Objective | Description of risk event | Owner of the risk | Cause(s) | Effect on timing of activities | Effect on budget of activities | Effect on achieving results | Action required | Likelihood1 | Consequence2 | Assessment3
1 | To deliver the project in the agreed time schedule | Signature of the contract later than anticipated | Financial manager | Delay in delivering supporting documents to MA by some beneficiaries | None | Prices for equipment have increased | None | Revision of the budget | Likely | Minor | Medium
2 | To achieve project operational objectives | Changes in the water legislation | Project manager | New law approved in the national parliament in one country | Need to revise activities to ensure compliance with new legal framework | Need to involve a legal advisor | Positive | Revision of the work plan and inclusion of new line in budget | Likely | Major | High
3 | To deliver good quality reporting for Managing Authority | Low-quality input from some beneficiaries to project and financial managers | Project and financial managers | Little experience in project management | More time devoted by project & financial managers and delays in delivery of reports | Delays in receiving the grant payments, which may lead to cash shortages | Potential late delivery of goods and services may reduce the capacity to achieve results | Well-prepared kick-off meeting and on-going support to all beneficiaries | Possible | Major | High
4 | To minimse the amount of ineligible expenditure | Poor understanding of all the applicable rules by beneficiaries | Financial manager | Changes in rules compared with previous projects not identified | None | Less grant received may prevent full absorption of funds if no additional co-financing is found | Less funds available may prevent purchasing necessary goods and/or services | Training to financial managers of all beneficiaries and on-going support | Possible | Moderate | Medium