## Slide 1: Training for beneficiaries 2nd Call for proposals Joint Operational Programme Black Sea Basin 2014-2020 Narrative reporting
25 November 2020

## Slide 2: Narrative Reporting
References:
Grant contract: Article 5 - Obligation to provide information and reports
“The progress report, covering every 4 months of the implementation period of the project, shall be submitted no later than 30 days after the above period has elapsed. If there is an overlapping between the months when the progress report and the interim report or the final report is due, only the interim or the final report shall be submitted.”
Partnership Agreements: Progress reports: 5.8: The progress report, covering every 4 months of the implementation period of the project, shall be submitted within […].
MA Instruction no 26 from 23 September 2020 to the beneficiaries of the 2nd Call for Proposals of the ENI CBC Black Sea Basin Programme 2014-2020 regarding the submission of the 4 months progress report (https://blacksea-cbc.net/black-sea-basin-2014-2020/reference-documents/ )

## Slide 3
Reporting rules
When?
In 30 days after completion of a period of 4 months of implementation – For the progress report;
within 90 days following the end of the reporting period (until the part of the expenditure actually incurred and paid which is financed by the MA is at least 70 % of the previous payment);
no later than six months after the end of the implementation period.
How?
Using the Template attached to Instruction no 26;
Where?
By eMS Mailbox to the JTS project officer
What is important to remember?
The information must be consolidated at project level and each partners involvement should be easy to identify;
All Sections must be filled in;
All delays must be justified and proposed measures must be described;
Don’t forget to attach the relevant documents for the narrative reporting (as per PIM);
Use the optional Checklist for the narrative report.

## Slide 4
Reporting rules
Progress report
Describe the progress registered only in the reported period
Do not attach other documents that are not requested!
Do not forget to update the Supplementary information Section – Procurements!
Interim and final report
Describe the progress from the beginning of the project implementation until the end date of the reporting period
Attach evidences for all deliverables!

## Slide 5
If you still need support for filing in the narrative reports, please consult us:
alla.nastych@bsb.adrse.ro
anamaria.munteanu@bsb.adrse.ro
elena.veselovskaia@bsb.adrse.ro
georgiana.bratu@bsb.adrse.ro
nicolae.minculescu@bsb.adrse.ro