## Slide 1: Training for beneficiaries 2nd Call for proposals Joint Operational Programme Black Sea Basin 2014-2020 Contract modification
26 November 2020

## Slide 2
Notifications
Who may initiate the notification? | Lead Beneficiary (or Beneficiary through the Lead beneficiary)
How? | A written request addressed to the JTS, by email (preferably using eMS email) 1 - 4 WITHOUT additional written confirmation from JTS 5 – 8 WITH written confirmation from JTS
When? | At least 10 working days before the date on which the changes shall be implemented
In which case? | 1. Change of the contact person of the Lead Beneficiary/beneficiaries 2. Change of the legal representative of the Lead Beneficiary/beneficiaries 3. Change of the EUR bank account/national currency bank account of the Lead Beneficiary I Beneficiaries 4. Change of the address of the Lead Beneficiary/Beneficiaries 5. Change of the name of the controller of the Lead Beneficiary/beneficiaries 6. Minor changes in the Work plan section of eMS: they may be related either to a change of format or to rescheduling of activities/deliverables, correction of errors. These changes should not have an impact on the main objectives of the project and/or on the total project duration. 7. Correction of inconsistencies between or within different eMS sections of the project; 8. Minor transfers of amounts between items within the same main budget heading, not having a major impact on the latest approved eMS version of the Budget, which may otherwise be subject to an Addendum.

## Slide 3
Addendum
Who may initiate the addendum? | Lead Beneficiary (or Beneficiary through the Lead Beneficiary); Managing Authority or the Joint Technical Secretariat
How? | By sending the proposed addendum to the JTS
When? | 45 days before the date on which the amendment should enter into force, or no later than 2 months before the end date of the implementation period.
In which case? | Changes of the duration of project's initial implementation period (extension of the implementation period). Changes in the beneficiary's organization or replacement of a beneficiary in the project Reallocation of costs between the main budget headings, in case of one Beneficiary or more, and other budget amendments which cannot be subject to a Notification by having a higher potential of altering consistently the latest approved version of eMS project. Reallocation of costs between partners Modification of the Human resources heading positions in the way of deleting or adding new positions in the project team Major changes in the Workplan of the latest approved version of eMS project Changes of the initial conditions set within the preliminary project design phases (e.g. feasibility study for projects with infrastructure and works)

## Slide 4
How to estimate when to send a request for modifications?
In case of a Notification: 10 days from Step 1 – Step 3
1. Submission of the request to JTS
2. JTS analysis/
Clarifications
3. Approval of the new version of the AF
3. Open modifications request in eMS
4. Making the changes in eMS

## Slide 5
How to estimate when to send a request for modifications?
In case of an Addendum: 45 days from Step 1 – Step 8
1. Submission of the request to JTS
2. JTS analysis/Clarifications
3. Open modification request in eMS and operating the changes
4. Analysis of the changes by JTS officer
5. Submission of the request by the JTS officer to MA
6. Analysis of the request by MA/
Clarifications
7. Signature of the Addendum at MA
8. Signature of the Addendum by the LB

## Slide 6
Think Twice!
Act Once!