## Slide 1: Training for Controllers Black Sea Basin 2014-2020 Reporting
27 November 2020

## Slide 2
MANDATORY TOOLS FOR CONTROLLERS
Interim/Final Report
Instruction no 19 from October 2019
Annex 5- Guide on reporting in the eMS
GRANT CONTRACT
https://blacksea-cbc.net/
Project Implementation Manual (last approved revision)
PIM Annexes (last approved revision)
Instruction no 27 from 15 October 2020
Communication and Visibility Manual JOP BSB 2014-2020
eMS Manual for CCPs and Controllers
Instruction no 15 from 2018 and its Annexes

## Slide 3
REMEMBER
Interim report (both narrative and financial parts)
70% of the advance payment has been spent/ half of the implementation period has elapsed
90 days
End of the implementation period
6 months
Final report ( both narrative and financial parts)

## Slide 4
Narrative report (part of the interim/final report)
Narrative report
Progress in implementation for the period starting the first day of the project implementation until the date foreseen in the eMS (Application Form – reporting period) for submitting the interim report/or until the last date of project implementation period (final report). The narrative report shall contain detailed information on the implementation of project activities, on indicators, outputs, deliverables, project’s potential impact and its sustainability (includes documentary evidence of outputs, documentary evidence of deliverables, promotional materials).

## Slide 5
List of Expenditures
The following provisions should be respected when filling in LoE:
The expenditures - within the reporting period of the report
Expenditures - reported per Budget lines and Group of Activities;
For staff costs, each item in the LoE is separated per person/per month and staff costs are declared under the GA Management unless they are budgeted under other GAs due to national legislation or the organization’s internal rules.
For Travel and accommodation - expenditure are reported per person.
Costs outside programme area have to be declared according to the „Expenditure Outside (The Union Part Of) The Programme Area” section and ticked in the LoE (if the case).
All the sections of LoE have to be filled in.
Expenditures declared under the budget lines “External Expertise and services”, “Equipment” and “Infrastructure” should be linked to the Procurement section/Supplementary Information (Annex 5 sections 2.7 and 4.3.2)
Please note that if travel and accommodation expenses for guests have been included in the budget under the Expertise and External Services budget line, these expenses should be reported accordingly. The relevant procurement rules must also be observed and applied when concluding service contracts.
Financial reporting is done through the List of Expenditures (LoE) section in eMS.
Financial report

## Slide 6
Supporting documents required for expenditure verification
Supporting documents section 6.5.3 from Project Implementation Manual (PIM)
Instruction no 15/2018 - Annex 3: Indicative list of supporting documents
All documents must be scanned preferably in black and white and at a resolution of 300dpi.
The files attached will be named in English in accordance with the relevant content of documents (e.g: invoice of the conference held at/on)
Upload section of the List of expenditure: e.g.Staff cost – payrolls, documents proving the payment
Section 4.3.2 of Annex 5-Guide on reporting in the eMS
Supplementary information /Procurements Section: all the procurements documentation.
Section 2.7 of Annex 5-Guide on reporting in the eMS
Attachment section of the Partner Report: e.g.Staff cost – appointment decisions, employment/work contracts, photographs,
Section 4.3.4 of Annex 5-Guide on reporting in the eMS

## Slide 7
Expenditure verification – aspects that need to be emphasized
2. For the purpose of reporting, conversion into euro shall be made using the monthly accounting exchange rate of the European Commission of the month during which the expenditure was submitted for verification, exchange-rate losses being non-eligible costs.
1.All evidences and supporting documents have to be verified in relation to the expenditure declared in the report.
3. The confirmed FLC certificate has to be uploaded in the eMS, scanned and signed. Also, have to be uploaded in the eMS, scanned and signed checklist, scanned version of the request for clarification and the answer of the beneficiary.

## Slide 8
4.All the sections of the FLC certificate have to be considered and filled in :
Bank account
Partnership agreement
Format of documents
VAT
Details about the partner
Should be mentioned the date in which the clarifications were asked and the date when the answer to clarification was received
Clarifications
Expenditures incurred outside eligible area of the programme
The location of the activity is the decisive factor when determining whether the implementation of an activity is outside the Programme area
5. Reporting rules have to be met:
Should be declared in original currency of the document
Expenditures
Declared expenditure
Expenses have been correctly allocated to the relevant groups of activities (Work Package in eMS)

## Slide 9
Joint Technical Secretariat
48A Tomis Boulevard
Constanta, Romania
Phone: +40 341 452 836
Fax: +40 341 452 841
E-mail: office@bsb.adrse.ro
firstname.surname@bsb.adrse.ro