## Slide 1
NARRATIVE REPORTING
HOW TO ORGANISE, STEPS, CONTENT, HOW TO REPORT IN EMS, ATTACHMENTS
14 JUNE 2021

## Slide 2
Content of the Narrative Part
of the Interim Report
Progress in implementation for the period starting the first day of the project implementation Contract until the last day of the interim reporting period
Detailed information on the implementation of project activities, on indicators, outputs, deliverables, project’s potential impact and its sustainability
All beneficiaries have to provide clear details on how complementarities/synergies are being considered during implementation.
Justify any deviation and in case of delays, explain how the delayed activities, deliverables and outputs will be completed
Please provide full and comprehensive description of progress achieved and do not make cross references to progress reports, as controllers are not able to see them.

## Slide 3: Report Sections
Main achievements: refer to the most significant achievements the project registered since the beginning till the last day of the period for which the Interim report is prepared (focus on the implementation groups of activities)
Specific objectives: select the appropriate level of achievement and describe the progress made towards their achievement in Period for which the Interim report is prepared
Target groups: correlate the values with the ones reported in the previous Progress Reports
Problems and solutions: describe any problems you encountered as well as the solutions found to mitigate potential risks
Horizontal principles: select the appropriate level of achievement and describe the relevant implemented activities in this respect

## Slide 4: WORK PACKAGES Section
WP description: describe the progress and partners’ involvement; justify delays, describe encountered problems and present applied solutions
Outputs: select the appropriate status, insert appropriate values under “achieved in this report” (pay attention to the initially planned target values), upload output evidence if finalized in the period for which the Interim report is prepared
Activities: select the appropriate activity status
Deliverables: select the appropriate status; upload the deliverable evidence (if finalized till the end of the reporting period for which the Interim report is prepared); shortly present the progress made towards its completion

## Slide 5: ATTACHMENTS Supporting documents
Annexes to the interim report:
 Declarations of the Lead Beneficiary/Beneficiary (see Annexes 7 and 8 to Instruction of the MA no. 15);
 Updated procurement plan (see Annex no.4 to PIM);
 Documentary evidence of outputs and results;
 Documentary evidence of deliverables;
 Informative and promotional materials;
 Standard Request for Payment (see Annex IV to grant contract);
 Financial Identification Form (FIF), if modified from the one attached to the Grant contract;
Photos and/or video capture from events/meetings organised within the project;
 Photos with equipment/supplies purchased by the project (results of works/spaces refurbished or any endowment if the case may be);
 Financial supporting documents;
 Documents related to public procurements;
 Expenditure verification reports/ FLC certificates.

## Slide 6
Use the Annex 9 “Checklist Beneficiaries _Narrative.doc)” of the Project Implementation Manual, developed as an optional self-verification tool prior to the submission of the report!
Final Check

## Slide 7
JTS PROJECT OFFICER :
GEORGIANA BRATU
Joint Technical Secretariat
48A Tomis Boulevard
Constanta, Romania
Phone: +40 341 452 836
Fax: +40 341 452 841
E-mail: office@bsb.adrse.ro
firstname.surname@bsb.adrse.ro

## Slide 8
Questions/topics from beneficiaries (1)
Instructions regarding the procurement plan and procedures
What is the role of the project assistant in the interim report?
Can we buy services or goods from university trade organizations?
What is the real possibility that the progress reports will return to the initial format of eMS?
In case the implementation period changes (extension by 6 months) does the deadline for the preparation and submission of the interim report change?
We would like to learn more about single tender procedures (both for services and supplies)
More detailed information to work with eMS –esp. downloads
What are Lead Beneficiary's obligations and main responsibilities in this report?
How is the quality of deliverables assessed?
How detailed should the interim report be?

## Slide 9
Questions/topics from beneficiaries (2)
11. In what form should the narrative report be made?
12. Details about the way of filling the interim report, terms, deadlines, etc.
13. How can be defined the Project Output Indicator and Targets Level of Achievement?
14. How can we proceed when the size of the deliverables is exceeding the maximum size accepted by the eMS system?
15. Should all partners upload on eMS the deliverables that are involved in (along with submitting the description of their contribution), or the WP leader only to avoid duplications?
16. Who will sign the Interim Report?
17. It is possible to access the eMS platform for initialization?
18.The Lead Beneficiary will have to submit an Interim report as Lead partner and as project partner as well ?